## Actuals 2026
KPI Name | Perspective | Target | Unit | Lower is Better | Weight % | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026
Average downtime for check type | Customer |  |  | Yes |  | 1) GHP: 600 Hrs+1 Year insp+TGB replacement (Planned down time: 10 days / Actual down time: 09 days 2) GHU 1 Year insp+300 Hrs insp+Libya ferry prep (delayed by 19 days due to pending delivery of M/R blade and Fuel Tank. | 1) GQG-300 Hrs inspection -delayed by 1 day due to pending CAMO reply to release the aircrft for test flight (Drive shaft balance weight missing) | 1) GHV: 300 Hrs+components +TGB fitting Inspection-delayed by 4 days due to pending delivery of Tail Rotor Blade & due to war situation 2) GHJ - TGB green run+600 Hrs inspection - Delayed by 22 days due to War situation
Flight Delays Percentage- Engineering | Customer | 5 | % | Yes |  | 1.9% | 2.8% | 8,33%
# Level 1 Audit Findings – ENG | Customer | 0 | # | Yes |  | 0 | 0 | 0
% staff with mandatory training in date | Learning & Growth | 95 | % | No |  | 100% | 96.5% | 90.5%
% staff validated as competent AMOS users | Learning & Growth | 80 | % | No |  | 100% | 100% | 100%
Repetitive defect rate per 100 flights | Internal Process | 1 | # | Yes |  | 4 | 1 | 0
#MEL same ACFT Events | Internal Process | 2 | # | Yes |  | 03 events over 2 MEL same ACFT | 01 evenet over 2 MEL same ACFT | 01 evenet over 2 MEL same ACFT
# RIE event ≠ARCFTS Events | Internal Process | 2 |  | Yes |  | 02 RIE event ≠ARCFTS | 02 RIE event ≠ARCFTS | 01 RIE event
Robbery Approval | Internal Process | 30 | # | Yes |  | 13 | 24 | 6
Critical spares PR Raised on Time | Internal Process | 90 | % | No |  | 1) D2-EQN: Engine (AOG Req date: 06-Jan-2026 / Received date: 04-Feb-2026) | 1) A7-GAA: APU (AOG Req date: 01-Feb-2026 / Received date: 12-Feb-2026) 2) A7-GAA: CABIN FAN(AOG Req date: 19-Feb-2026 / Received date: 19-Mar-2026 3) A7-GAA: SWITCH CABIN DOOR(AOG Req date: 9-Feb-2026 / Received date: 21-Feb-2026 | 1) A7-WAW: Engine (AOG Req date: 24-Mar-2026 / EDD: To be provided by Procurement
Review Process and Procedures update rate % | Internal Process | 90 | % | No
Budget Adherence % | Financial | 100 | % | Yes |  | 158,694.83 0.08% of the Annual Capex Budget | 602,586.72 0.32% of the Annual Capex Budget | 361,975.32 0.19% of the Annual Capex Budget

## Historical
KPI Name | Perspective | Target | Unit | Lower is Better | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025
Average downtime for check type | Customer |  |  | Yes
Flight Delays Percentage- Engineering | Customer | 5 | % | Yes
# Level 1 Audit Findings – ENG | Customer | 0 | # | Yes
% staff with mandatory training in date | Learning & Growth | 95 | % | No
% staff validated as competent AMOS users | Learning & Growth | 80 | % | No
Repetitive defect rate per 100 flights | Internal Process | 1 | # | Yes
#MEL same ACFT Events | Internal Process | 2 | # | Yes
# RIE event ≠ARCFTS Events | Internal Process | 2 |  | Yes
Robbery Approval | Internal Process | 30 | # | Yes
Critical spares PR Raised on Time | Internal Process | 90 | % | No
Review Process and Procedures update rate % | Internal Process | 90 | % | No
Budget Adherence % | Financial | 100 | % | Yes